## Blad1
Sprint Backlog, Iteration #0
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort per Task | Priority A - E
|  |  |  | (in hours) | (A is highest, E is lowest)
Map | Background (done) | Matt | Matt | 2 hours | E
| GUI | Matt | Matt | 2 hours | D
Track | Designing the track | Joost | Joost | 4 hours | A
| Automating track positions |  | Matt&Joost | 4 hours
Shooter | Mouse events | Callum | Callum | 2 hours | D
| Key events (done) |  |  | 1 hour | A
| Shooter position (done) |  |  | 1 hour | A
| Rotation (done) |  |  | 1 hour | A
| Shooting (done) |  |  | 1 hour | A
Marbles | Marble design | Callum | Callum | 1 hour | A
Intersection | Intersection | Rodrigo | Rodrigo | 4 hours | A
Lives | Lives | Xinyue | Xinyue | 1 hour | B
Scores | Scores | Xinyue | Xinyue | 2 hours | A
E.o.G. | End of game conditions | Xinyue | Xinyue | 2 hours | A
Project: Zuma Deluxe
Group: Deluxe